## BFIN Action Log
BFIN Action Log (NB RAG = progress not risk) - please filter on column H status to view open actions | [6 empty] | Filter here
Ref | Action | Who | Date logged | Target date for completion | Outcome/notes | End of 23/24 update where applicable | Status | RAG
53 |  |  | 2024-06-13
52 |  |  | 2024-06-13
51 | Send out round up request by 24th June - deadline end of June for members to send updates | BCVS (KB) | 2024-06-13 | 2024-06-24 |  |  | Open | Amber
50 | Circulate links to July and September BFIN meetings asap after June meeting | BCVS (KB) | 2024-06-13 | 2024-06-14 |  |  | Open | Amber
49 | Circulate link to June Round up first week of July | BCVS (KB) | 2024-06-13 | 2024-07-05 |  |  | Open | Amber
48 | Contact Green core to identify whether direct delivery of surplus to hubs possible | MKS | 2024-05-15 | 2024-05-30 | Positive outcome and free deliveries to hubs now in place |  | Closed | Green
40 | Collate monthly round-up of member and BFIN relevant news each month - deadline by last working day of each month and to go out the following week - first edition to be circulated | All BFIN members | 2024-03-30 | 2024-05-03 | Actioned |  | Closed | Green
35 | NOW EAT / NOW Church Presentation to be added to BFIN section on BCVS website | BCVS (KB) | 2024-03-26 | 2024-04-04 | Added |  | Closed | Green
36 | BCVS to update action log with actions agreed at March BFIN meeting and forward to KB to go onto website - link to be sent to all BFIN members | BCVS (AB) | 2024-03-26 | 2024-04-04 | Actioned |  | Closed | Green
37 | Type up 24/25 priorities proposed at March meeting by members into 24/25 action plan template and circulate to members for comment | BCVS | 2024-03-26 | 2024-04-10 | Actioned |  | Closed | Green
38 | Identify budget to resource production of BFIN Book (To showcase and provide information on BFIN member support available re food insecurity and sustainability | BCVS (AB) | 2024-03-26 | 2024-04-04 | Actioned and final template to be shared in June meeting |  | Closed | Green
39 | All partners that wish to be included in BFIN Book to provide information as per spec circulated by BCVS | All BFIN members | 2024-03-26 | 2024-04-10 | Deadline passed, 15 entries for edition one |  | Closed | Green
41 | All partners to send updates by end of each month - either by email or web form or similar to be set up by BCVS | All BFIN members | 2024-03-26 | 2024-04-30 | Reminders to go out one week before month end |  | Open | Amber
42 | Identify online collaboration space fit for purpose | All BFIN members | 2024-03-26 | 2024-04-26 | Currently using website, round ups and newsletter for comms |  | Open | Red
43 | Confirm date for early May online meeting to review BFIN Book and outstanding actions | BCVS | 2024-03-26 | 2024-04-04 | Actioned |  | Closed | Green
44 | All BFIN members to feedback on member proposal to move to quarterly 2 hour face to face BFIN meetings to include spotlight on member, examples of national good practice, and collaboration and networking - online links to be made available for first hour of meeting for those who can't travel and presentations to be recorded | All BFIN members | 2024-03-26 | 2024-04-08 |  |  | Closed | Green
45 | Request confirmation from current BFIN members of who would like to stay on mailing list | BCVS | 2024-03-26 | 2024-04-11 | Actioned |  | Closed | Green
46 | Create webform for BFIN membership to enable new members to join and add to BFIN news section of newsletter | BCVS | 2024-03-26 | 2024-04-11 | Actioned - to be standing item in newsletters |  | Closed | Green
47 | NSFN organising food summit for World Food Day 16th October - partners who wish to attend please save the date - action to be added to action log | All BFIN members | 2024-03-26 | 2024-04-04 | Added to log and included in updates |  | Closed | Green
32 | NCC Food JSNA to be circulated once published | NCC PH | 23/01/2024 | As soon as published | Ciculated in April update |  | Closed | Green
27 | BCVS to identify appropriate contact for the Curriculum Lead at the Skills Hub | BCVS (AB) | 2024-01-23 | 2024-02-29 | AB signposted to Tim Gladman, TG confirmed he is current lead whilst Skills Hub Manager recruited - TG to confirm when in post - have had to go out several times - follow up emails sent in April and June |  | Open | Amber
29 | FareShare to confirm who all 22 members are in Bassetlaw if possible (some non Food hubs) | Fareshare | 2024-01-23 | 2024-02-29 | Complete and circulated - now 14 members and food hubs |  | Closed | Green
34 | Kings Coronation Fund further details to be circulated as soon as available | FareShare | 2024-01-23 | As soon as received | AH confirmed that it will be distributed via FairShare member networks and that memberships available - more info to be circulated when available |  | Open | Amber
28 | BCVS to escalate need for food /nutrition education as part of Bassetlaw Common Induction Pack | BCVS (AB) | 2024-01-23 | 2024-02-29 | Done |  | Closed | Green
30 | Information on community grants round 3 to be circulated once round open | BCVS | 2024-01-23 | 2024-02-29 | Done |  | Closed | Green
31 | Best Food Forward Training session offer to be recirculated | BCVS | 2024-01-23 | 2024-01-29 | Done |  | Closed | Green
1 | BFIN members to feedback on description of BFIN, BCVS to update description following feedback and discussion at the meeting. | All | 28/11/2023 | 31/12/24 | About BFIN ¦ Bassetlaw CVS (bcvs.org.uk) |  | Closed | Green
2 | Book on to Bid Writing course asap if you want a free place as will be opened to non members next week | All | 28/11/2023 | 26/01/24 | book here - only 2 spaces left |  | Closed | Green
3 | BCVS to review BFIN member list and request confirmation of wish to remain on mailing list | All | 28/11/2023 | 26/01/24 | https://www.bcvs.org.uk/bfin-members - also need to identify who is missing and add details if appropriate | Emails sent to all members previously - new action agreed at March 24 meeting to be added below | Closed | Amber
4 | FareShare to supply details of which Bassetlaw Food Hubs will be open during the Christmas School Holidays if they have this detail – BCVS to promote via social media and other channels | Fareshare, BCVS | 28/11/2023 | 1/12/24 | Information confirmed by Schools |  | Closed | Amber
5 | Marzena Karp Singh (MKS) as BCVS Community and Group Development Worker will provide support for development of new ABL slow cooker courses in Manton over rest of year (no time to discuss social eating in Nov BFIN meeting) | BCVS (MKS) | 28/11/2023 | 23/01/24 | Marzena to add latest brief details here | Marzena has added details to BCVS newsletters for each school holiday | Closed | Green
6 | BDC officers to provide details of any details of any existing links and focus on food insecurity work if possible either separately or via partner update link below under action 23 | BDC | 28/11/2023 | 23/01/24 |  | New BDC officer Katie Sharman to be BDC rep to BFIN from March 24 onwards | Closed | Green
10 | BCVS to circulate information about Bread and Butter Work in the region – not operating in Bassetlaw but operating in Newark and Sherwood: Award-winning affordable food project expands to the East Midlands — The Bread and Butter Thing | BCVS | 28/11/2023 | 2023-12-12 | The Bread and Butter Thing | Included in BFIN mailings | Closed | Green
12 | BCVS to share infographic of Children’s Kitchen work | BCVS | 28/11/2023 | 5/12/23 | Shared via link here: https://www.bcvs.org.uk/bfin-impact |  | Closed | Green
13 | BCVS to share link to film of SAF work on Best Food Forward with key health partners with copy to Lauren – please find additional details attached. | BCVS | 28/11/2023 | 12/12/23 | Uploaded by SAF and link shared by BCVS with network , SFN and BPBP |  | Closed | Green
14 | BCVS to escalate information on Food Standards Agency research published re impact of Cost of Living on food storage and cooking times safety and health impacts – thanks to Roger for sharing this, additional information also supplied by Roger post meeting as attached. | BCVS | 28/11/2023 | 29/11/2023 | Info sent 29/11/23. |  | Closed | Green
15 | BCVS to share links again to Community Grants information here – for more information please email communitygrants@bcvs.org.uk or ring 01909 47 61 18. | BCVS | 28/11/2023 | 28/11/23 | Done - also here https://www.bcvs.org.uk/ukspf |  | Closed | Green
16 | Any food hubs that want to purchase the staples bags @£5 each for service users to contact Melanie at Rhubarb Farm directly – 100 have been produced containing oil, spices, herbs, pasta etc at a value of £20 | ALL, RF | 28/11/2023 | 2023-11-28 | Request from Melanie not to promote more widely. |  | Closed | Green
17 | FareShare to share details of previous offers of surplus offers made by logistics companies which have had to be declined due to storage issues | FS | 28/11/2023 | Ongoing | Not yet received | FareShare confirmed no live offers, only frozen food is being turned down currently - confirmed this is stable/ ie will continue | Closed | Amber
20 | BFIN members to contact Anthony directly if interested in FareShare membership scheme as limited number of additional memberships currently available (provision of 1:4 ratio of cost to value of food provided) | All, Fareshare | 28/11/2023 | ongoing | AB met and discussed with RG at BFB | Information has also been shared with BFIN members via meetings and FareShare updates | Closed | Green
21 | BFIN members to provide details of logistics companies and contacts and BCVS will collate – joint BFIN approach needed once storage has been identified – also need to agree what the ask is – what type of food and what is not possible to take to avoid disposal costs. | All, BCVS | 28/11/2023 | ongoing | No details received | FareShare confirmed no live offers, only frozen food is being turned down currently - confirmed this is stable/ ie will continue | Closed | Green
22 | AB to contact Foodbank to offer meeting to discuss BFIN work and to flag above | BCVS (AB) | 28/11/2023 | 15/12/23 | AB met and discussed with RG at BFB - interested and supportive but no capacity to attend, needs to focus on delivery of BFB strategy |  | Closed | Amber
23 | All members in attendance provided a useful verbal update at the meeting. We would be grateful if you would provide a brief written update whether in attendance or note to be collated and shared with all members please by completing brief form by 1st December if possible | All | 28/11/2023 | 1/12/23 | Circulated and uploaded to BFIN resource page here https://www.bcvs.org.uk/bfin-meetings-minutes |  | Closed | Amber
24 | BCVS to circulate link to D2N2 AGM where interim CEO of EMCCA will be presenting. AB attending and will feedback at next BFIN. (Link circulated on 29/11) | BCVS (AB) | 28/11/2023 | 28/11/23 | Also mayoral event here https://www.nottinghampartners.co.uk/events/ | AB attended and fedback to BFIN at January meeting | Closed | Green
25 | BCVS to circulate details of next meeting to be hybrid in mid-January and to focus on goals and action needed to progress collective goals further – partner update link to be provided in advance to enable partner update to be shared with all | BCVS | 28/11/2023 |  | January 24 updates to be added by partners here please https://www.surveymonkey.com/r/BFIN_Update_Jan_24 |  | Closed | Green
26 | BCVS to set up a BFIN action log to enable updates to be noted throughout the year – to be formatted and clustered under year one and year two goals from the BFIN action plan and designed to keep progress and actions moving forward. | BCVS | 28/11/2023 |  | This document. Clustering ignored in favour of target date. |  | Closed | Green
7 | BCVS to email BAC and NHS Place Comms to provide lists of all local farms if possible connected to Farm Start and any other local Farm projects – BDC to provide details if they have lists of farms | BCVS | 28/11/2023 | 05/12/23 | Request for information sent in December, plus follow up. AB reached out to BAC who are involved in Focus on Farmers and who have offered to provide an update at June meeting | To follow up again | Open | Amber
8 | All BFIN members to confirm if they receive any food supplies from local growers please by emailing MKS with details to support action to map which local growers are already supporting food insecurity work – either from community allotments or local farms and which are missing | All, BCVS (MKS) | 28/11/2023 | 23/01/24 | No replies received - closing due to no response - consider different way of mapping at future meeting | No replies received | Closed | Red
9 | BCVS to request details on Newark and Sherwood Case study presented to the Notts Sustainable Food Network earlier this year – can’t find information on N&S DC website but info is still on this site: Allotment owners can share unused produce under new council scheme ¦ West Bridgford Wire | BCVS | 28/11/2023 | 12/12/23 | Request for information sent to jenny.palmer@newark-sherwooddc.gov.uk - Jenny hasn't been available on dates of meetings, invitation to September meeting sent | Jenny happy to present however hasn't been available on BFIN meeting dates so far - BCVS to follow up for 24/25 | Open | Amber
11 | BCVS to map community food storage locations, type (refrigerated, frozen, ambient) capacity, organisation name and access /space available through a survey to VCSE sector and other key community partners. FareShare to please provide any Baseline info they have in first instance before survey to fill gaps is circulated. If any partners have examples of how this is categorised or mapped elsewhere please share with BCVS. | BCVS | 28/11/2023 | 2023-12-05 | Requests for information sent - no details received - closing due to no response - consider another way of mapping in future if partners wish to prioritise this again | Some details received from FareShare - not other details received to date | Closed | Red
18 | Any partners needing BCVS support with recruitment of volunteers to add vacancies here please | ALL, BCVS | 28/11/2023 | 28/11/23 | add vacancies here please |  | Closed | Amber
19 | Partners to provide information on any farms that have previously offered surplus which needs to be picked for follow up contact by BCVS – MKS has checked with SH who has no details of Farm work or offers but has a list of allotments | ALL | 28/11/2023 |  | BCVS - MKS has checked with SH who has no details of Farm work or offers but has a list of allotments - closing as no partners have any info and RF not able to provide |  | Closed | Amber
33 | January meeting presentations to be added to BFIN section on BCVS website | BCVS (KB) | 23/1/24 | As soon as received |  |  | Closed | Green
NB - Add new actions to top of sheet only please